## Guidance
Guidance
Benefits Tracking Tool (e-Rostering) How to use: 1) Go to the 'Benefits_Register' tab and assign a Benefit Owner for each benefit. 2) In 'Catalogue_Measures', set Unit, Polarity, Baseline and Target for each measure. 3) In 'Monthly_Data', add a new row each reporting period (e.g., 2026-01) with Actuals. 4) The 'Performance' and 'Dashboard' tabs update automatically (green = on target). Tips: - Polarity: choose 'Higher is better', 'Lower is better', or 'Within range'. - Period format: YYYY-MM (e.g., 2026-01). - Do not delete rows inside tables—append new rows instead.

## Catalogue_Benefits
Benefit_ID | Benefit_Code | Benefit_Name | Category_Number | Category_Name | Description
B001 | 1.1 | Reduction in bank nursing cost | 1 | Reduction in bank nursing cost | - more efficient roster planning and use of substantive staff - reduced bank and agency demand - removal of unused contracted hours - creation of an up-to-date clinical demand driven roster - more proactive planning around the use of agency staff, resulting in reduced rates - better verification of bank and agency shifts & enhanced hours to ensure timesheets match shifts worked
B002 | 2.1 | providing better information on which to plan resource allocation demonstrating best utilisation of available skills | 2 | Ease of access to workforce information
B003 | 2.2 | providing evidence that will inform strategic workforce planning | 2 | Ease of access to workforce information
B004 | 2.3 | increasing timeliness of information to monitor absence and forward plan operationally | 2 | Ease of access to workforce information
B005 | 2.4 | realising the potential for benchmarking with other organisations using the same software | 2 | Ease of access to workforce information
B006 | 2.5 | clarity of rosters in an easy read format accessible by all staff electronically | 2 | Ease of access to workforce information
B007 | 3.2 | increasing the efficiency of the interface with the payroll service, automation with the Electronic Staff Record (ESR) | 3 | Improved payroll accuracy
B008 | 3.3 | improving financial forecast based on fact not accruals | 3 | Improved payroll accuracy
B009 | 3.4 | reduction of overpayments | 3 | Improved payroll accuracy
B010 | 4.1 | monitoring and alerting the user and manager to non-compliance on the working time directive | 4 | Compliance with regulatory requirements
B011 | 4.2 | monitoring shifts against minimum requirements (people and skills) | 4 | Compliance with regulatory requirements
B012 | 5.1 | improving work/life balance through the early production of rosters | 5 | Flexible working
B013 | 5.2 | reduction of individual time spent adjusting manual rosters within their own time | 5 | Flexible working
B014 | 5.3 | improving work/life balance through fair allocation of time for training, rest, annual leave etc. | 5 | Flexible working
B015 | 5.4 | improving team morale by removing conflict/tension over shift allocation | 5 | Flexible working
B016 | 6.1 | enabling the appropriate use of staff resources - the right person, with the right skills, looking after the patient - and so reducing clinical risk and maximising service potential | 6 | More productive use of staff | improved clinical governance through enhanced control of staffing levels and skills and improved assurance controls in the management of issues. effective management of staff downtime for leave, study and management time. elimination of paperwork related to sickness and absences, vacancy management, and timesheets for unsocial hours, bank and agency shifts. staff downtime data can be used to identify trends. effective rostering of substantive staff reducing the demand for temporary staff or overtime.
B017 | 6.2 | maximising the impact of revised ward skill-mix, with consequent improvements in the quality and safety of patient care | 6 | More productive use of staff | improved risk management: i) before an incident, through enhanced control of staffing levels and skills ii) after an incident, through improved audit trails of actual nursing levels required and present, for incident reporting. greater visibility and control over staff competencies and mandatory training. can set ward performance benchmarks against which the draft, approved and worked rosters can be measured and managed.
B018 | 6.3 | acting as a lever for the modernisation of culture, attitudes and working practices among teams a strategy based on evidence which can be benchmarked internally and nationally | 6 | More productive use of staff | [complex and difficult benefit to measure…who benefits from this?].
B019 | 7.1 | improving the efficiency and effectiveness by reducing the amount of time currently spent by managers and support staff on administrative duties as required by the current paper systems | 7 | Greater management control and reduction in time spent on administration | Ward managers can sign off their electronic rosters which removes the manual process to sign off paper timesheets. Ward administrative time savings from reduced payroll administration and queries. Auto rostering potentially increase number of shifts filled. Improved people management processes on wards e.g. sickness reporting, vacancy monitoring/filling etc.

## Catalogue_Measures
Measure_ID | Benefit_ID | Measure_Name | Unit | Polarity | Baseline | Baseline_Period | Target | Target_Period | Frequency | Data_Source
M001 | B001 | planned roster costs vs. actual roster costs (split by substantive, overtime, bank and agency spend) |  | Higher is better |  |  |  |  | Monthly
M002 | B001 | staff costs vs. budget (split by substantive, overtime, bank and agency spend) |  | Higher is better |  |  |  |  | Monthly
M003 | B001 | % of substantive staff hours utilised |  | Higher is better |  |  |  |  | Monthly
M004 | B001 | # duties assigned to the wrong type/grade of staff (e.g. HCA duty covered by RN) |  | Higher is better |  |  |  |  | Monthly
M005 | B001 | Spend on bank shifts and agency shifts per roster |  | Higher is better |  |  |  |  | Monthly
M006 | B001 | % staff paid incorrectly per roster or # payroll queries |  | Higher is better |  |  |  |  | Monthly
M007 | B016 | establishment skill mix equals roster skill mix |  | Higher is better |  |  |  |  | Monthly
M008 | B016 | # shifts that don't have a 'take-charger' |  | Higher is better |  |  |  |  | Monthly
M009 | B016 | % of unfilled shifts |  | Higher is better |  |  |  |  | Monthly
M010 | B016 | reduction in the number of untrained shifts being filled by trained staff. |  | Higher is better |  |  |  |  | Monthly
M011 | B016 | % shifts filled by bank and agency staff per roster |  | Higher is better |  |  |  |  | Monthly
M012 | B016 | % of substantive staff hours utilised |  | Higher is better |  |  |  |  | Monthly
M013 | B017 | # staff related incidents reported, or # of slips, falls, patient incidents per shift/per ward etc. |  | Higher is better |  |  |  |  | Monthly
M014 | B017 | % staff compliant to statutory and mandatory training |  | Higher is better |  |  |  |  | Monthly
M015 | B019 | time released from ward manager's day (measured by survey or observation) |  | Higher is better |  |  |  |  | Monthly
M016 | B019 | % of unfilled shifts |  | Higher is better |  |  |  |  | Monthly

## Benefits_Register
Benefit_ID | Benefit_Name | Category_Number | Category_Name | Benefit_Owner | Directorate_or_Service | Start_Date | End_Date | Realisation_Date | Realisation_Value | Notes
B001 | Reduction in bank nursing cost | 1 | Reduction in bank nursing cost
B002 | providing better information on which to plan resource allocation demonstrating best utilisation of available skills | 2 | Ease of access to workforce information
B003 | providing evidence that will inform strategic workforce planning | 2 | Ease of access to workforce information
B004 | increasing timeliness of information to monitor absence and forward plan operationally | 2 | Ease of access to workforce information
B005 | realising the potential for benchmarking with other organisations using the same software | 2 | Ease of access to workforce information
B006 | clarity of rosters in an easy read format accessible by all staff electronically | 2 | Ease of access to workforce information
B007 | increasing the efficiency of the interface with the payroll service, automation with the Electronic Staff Record (ESR) | 3 | Improved payroll accuracy
B008 | improving financial forecast based on fact not accruals | 3 | Improved payroll accuracy
B009 | reduction of overpayments | 3 | Improved payroll accuracy
B010 | monitoring and alerting the user and manager to non-compliance on the working time directive | 4 | Compliance with regulatory requirements
B011 | monitoring shifts against minimum requirements (people and skills) | 4 | Compliance with regulatory requirements
B012 | improving work/life balance through the early production of rosters | 5 | Flexible working
B013 | reduction of individual time spent adjusting manual rosters within their own time | 5 | Flexible working
B014 | improving work/life balance through fair allocation of time for training, rest, annual leave etc. | 5 | Flexible working
B015 | improving team morale by removing conflict/tension over shift allocation | 5 | Flexible working
B016 | enabling the appropriate use of staff resources - the right person, with the right skills, looking after the patient - and so reducing clinical risk and maximising service potential | 6 | More productive use of staff
B017 | maximising the impact of revised ward skill-mix, with consequent improvements in the quality and safety of patient care | 6 | More productive use of staff
B018 | acting as a lever for the modernisation of culture, attitudes and working practices among teams a strategy based on evidence which can be benchmarked internally and nationally | 6 | More productive use of staff
B019 | improving the efficiency and effectiveness by reducing the amount of time currently spent by managers and support staff on administrative duties as required by the current paper systems | 7 | Greater management control and reduction in time spent on administration

## Monthly_Data
Measure_ID | Period | Actual | Comment | Updated_By | Updated_Date

## Performance
Measure_ID | Measure_Name | Benefit_ID | Latest_Period | Latest_Actual | Target | Polarity | Variance | RAG